## All requirements
Requirement Tracking Sheet ( wherever required, Please look into the accomapnied HeliusHCMRequirements.doc and dashboard ppt for more details.)
S.No. | Date | Requirement type | Reuirement Main Category | Requirement Sub Category | Description | Owner | Remarks | Reference | Status
1 | 2018-05-24 | Functionality | Employee master | Employee assignment section | Add dropdown for client, group, subgroup, search option for SOW reference number/PO number | Shekhar | on employee assignment section, we also need to allow to select Client/ group/ subgroup & then SOW number ( with search capability on contract reference number/PO number or SOW number or plain select from SOW options.). perhaps validate if an existing employee is already assigned on it, hence in SOW section we need to ADD a select flag for “If SOW is valid for only 1 person or multiple persons”. Will not be available as part of June 1st week demo | from Shekhar's mail on 24th May | Not started | Not started | Not started | Not started
2 | 2018-05-24 | Functionality | Employee master | Employee assignment section | Payroll entity dropdown data: Nsearch, Marall, Helius, Dezire, Apar | Shekhar |  | Telecon on 24th May | Progress | Progress | Progress | Progress
3 | 2018-05-24 | Functionality | SOW master | SOW create section | separate field to capture whether the SOW being created is for single or multiple employees | Shekhar | creating a field Association Type: dropdown values (single, multiple) | Telecon on 24th May | Progress | Progress | Progress | Progress
4 | 2018-05-24 | Functionality | HR dashboard | Main Menu | Claims history and analysis - HR can view claims for selected period for analysis | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
5 | 2018-05-24 | Functionality | HR dashboard | Main Menu | Timesheets history and analysis -- HR can view past timesheets for any anaysis and investigation | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
6 | 2018-05-24 | Functionality | HR dashboard | Main Menu | Leaves history and analysis -- HR can view employee leaves for a selected period for any anaysis | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
7 | 2018-05-24 | Functionality | SOW journey |  | support for uploading SOW, signed SOW, PO, Contract | Shekhar | This was stated earlier but not made part of SOW section | Telecon on 24th May | Progress | Not started | Not started | Not started
8 | 2018-05-24 | Functionality | SOW journey |  | Upload draft SOW | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
9 | 2018-05-24 | Functionality | SOW journey |  | Upload signed SOW | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
10 | 2018-05-24 | Functionality | SOW journey |  | Upload contract | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
11 | 2018-05-24 | Functionality | SOW journey |  | Upload PO | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
12 | 2018-05-24 | Functionality | SOW journey |  | Modify SOW | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
13 | 2018-05-24 | Functionality | SOW journey |  | Renew SOW | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
14 | 2018-05-24 | Functionality | SOW journey |  | Change P & L Owner | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
15 | 2018-05-24 | Functionality | SOW master | SOW details section | SOW specific MIS | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
16 | 2018-05-24 | Functionality | SOW master | SOW create section | Early termination of SOW | Shekhar |  | Telecon on 24th May | Not started | Not started | Not started | Not started
17 | 2018-05-24 | Functionality | User access management | User type | User type = Client User role = Client - Finance Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
18 | 2018-05-24 | Functionality | User access management | User role | User type = Client User role = Client - Budget Owner | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
19 | 2018-05-24 | Functionality | User access management | User role | User type = Client User role = Client - HR | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
20 | 2018-05-24 | Functionality | User access management | User role | User type = Client User role = Client - Reporting Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
21 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - Administrator | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
22 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - Employee | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
23 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - HR Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
24 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - SOW Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
25 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - Account Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
26 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - Finance Manager | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
27 | 2018-05-24 | Functionality | User access management | User role | User type = Internal User role = Helius - HR - Recruiter | Shekhar |  | Telecon on 24th May | Progress | Not started | Not started | Not started
28 | 2018-05-24 | Functionality | User access management | Login screen | User type drop down with 'Client' and 'Helius' as values User roles dropdown with values as given in above cells | Shekhar | Depending on user type and user role selection, application opens up with appropriate UI having permissioned features for that user | Telecon on 24th May | Not started | Not started | Not started | Not started
29 | 2018-05-24 | Functionality | SOW master | SOW create section | GST can be monthly/quarterly etc.. | Parvathy | . In the SOWs, GST is included monthly. That is, 7% of monthly fee in Singapore. But I suppose if we are looking at a generic app, we should plan for tax that is not monthly but annual/ quarterly, etc. WE CAN COMPUTE THIS | Parvathy's mail on 24th May | Not started | Not started | Not started | Not started
30 | 2018-06-05 | Functionality | Employee master | Employee Create section | Employee ID numbering for all Helius employees -- As of now Singapore follows one convention where as India follows a different convention. Need to come up a single format for all Helius employees | Shekhar | More will be discussed on this after the ppt presentation on June 4th. 1. Disucss with Shashikala and shoot a mail to all concerned | Meeting on 18th May 2018 | Not started | Not started | Not started | Not started
31 | 2018-06-05 | Functionality | SOW master | SOW create section | Support for additional SOW types 'Fixed Price', 'Seat' | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
32 | 2018-06-05 | Functionality | SOW master | SOW create section | Support for additional field 'SOW Total amount' (Monthly* SOW duration + Onetime) | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
33 | 2018-06-05 | Functionality | SOW master | SOW create section | Change assocation type to Multiple resources (Yes or No) | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
34 | 2018-06-05 | Functionality | SOW master | SOW create section | Payment terms | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
35 | 2018-06-05 | Functionality | Employee master | Employee Personal Details | support for upload resume and upload offer letter | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
36 | 2018-06-05 | Functionality | SOW master | SOW create section | Add support for onboarding documents checklist, for uploading documents | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
37 | 2018-06-05 | Functionality | SOW master | SOW view | Add client, client group, client subgroup in employee assignment details section | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
38 | 2018-06-05 | Functionality | SOW master | SOW view | Support for searching SOW by Heliues SOW reference number, PO number, Auto suggestion | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
39 | 2018-06-05 | Functionality | SOW master | SOW view | Support for downloading SOW, Contract PO | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
40 | 2018-06-05 | Functionality | SOW master | SOW create section | Support for sofar invoiced, uninvoiced, remaining to be invoiced | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
41 | 2018-06-12 | Functionality | SOW master | SOW create section | Support for updating SOW, upload final SOW, Terminate SOW, upload contract, upload PO | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
42 | 2018-06-12 | Functionality | SOW master | SOW create section | Helius SOW reference number. Ex: New : DBS\GROUP\SUBGROUP\001\2018 Renew : DBS\GROUP\SUBGROUP\001\2018\REN. 1. Client abbrevation of 5 characters with all client group and subgroups 2. Will System generate the NO. with client level or groups level 3. What will we do with the historical sows? 4. Currently SOW refers the sow name. is there any consequencies | Shekhar |  | Telecon on 01-06-2018 | Progress | Not started | Not started | Not started
43 | 2018-06-12 | Functionality | Client master | Client Master | In client master ( need to run this by – Parvathy (for SOW ), Mayura( for invoicing), Account manager ( for other details), HR Manager (for client specific variations) *client short name (5 characters ) *client name *client master agreement reference *client master agreement expire on *upload master agreements *capture client logo Key Contacts *Key contacts at client (name role email phone user access (yes/no) *prepare table For user access – Yes, user to be able to access client dashboard at client level, group level sub group level User type – budget owner, timesheet approver or both * Create group and sub group *for each group and sub group one budget owner and multiple timesheet approvals Payment policy *client billing address *client invoicing contact name and email id phone no. *default client payment terms and conditions Timesheet policy *client timesheet (manual or automated) *Timesheet due to the timesheet approving manager *Manager approvals of timesheet due on this date Leave policy *default leaves details (link to employee) ( annual leave, medical leave, casual leave, maternity leave, paternity leave, compoff leaves allowed(yes-no), leave encashments *Appraisals of employee on completing 1 year or a fixed date Reimbursement Policy - Approval limit for timesheet approver - Reimbursement based on the cost - Do reimbursement require manager approval only and/or receipts - Category of Reimbursement types o Local travel o Intracity travel o Within country travel o International travel o Tickets etc., Please look at the ClientMaster.doc for the mockup UI | Shekhar | Please look at the ClientMaster.doc for the mockup UI | Meeting on 11-06-2018 | Not started | Not started | Not started | Not started
44 | 2018-06-12 | Functionality | Client master | Client Master | * Remove waterfall and agile, * Remove seniority * Include Start of first job (MMYYYY) * Add Role (display 2nd option after selecting 1st) *Developer *>Product Developer(multiple select) o Technical architect o UI/UX Designer o System Admin o Program Manager * Project Experience Type * Remove technology | Shekhar |  | Meeting on 11-06-2018 | Not started | Not started | Not started | Not started
45 | 2018-06-12 | Functionality | Client master | Client Master | ADD Employee T & C section * Leaves eligible – Annual, casual, medical * Training eligible – Yes / No if Yes, put a field * One time bonus eligible * Yes/No if Yes, put a date * Notice Period * Probation period * Reservist leave allowed – Yes/No | Shekhar |  | Meeting on 11-06-2018 | Not started | Not started | Not started | Not started
46 | 2018-06-12 | Functionality | common | common | Dynamic query based on role and technology and display employee work status, display salary, display years of experience and display project experience type, end customer and interaction exp. | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
47 | 2018-06-12 | Functionality | Employee master | Employee Personal Details | * Add the filter in employee search named Status – active and non*active status , by default it should be Active for HR and active and Ex*employee for Recruiter * Status – Active, Ex*Employee, On Notice Period * Update will be active for HR and inactive for Recruiter and Account Manager | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
48 | 2018-06-12 | Functionality | Batch jobs | Batch Jobs | * Upload timesheets | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
49 | 2018-06-12 | Functionality | Batch jobs | Batch Jobs | * Upload Paid claims | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
50 | 2018-06-12 | Functionality | Batch jobs | Batch Jobs | * Upload Payslips | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
51 | 2018-06-12 | Functionality | Batch jobs | Batch Jobs | * Upload Referral status | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
52 | 2018-06-12 | Functionality | Batch jobs | Batch Jobs | * Send Alert SMS | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
53 | 2018-06-13 | Functionality | Batch jobs | Batch Jobs | * Run 30/90/180 day Employee Feedback | Shekhar |  | Meeting on 12-06-2018 | Not started | Not started | Not started | Not started
54 | 2018-06-14 | Functionality | Employee dashboard | Claims | Employee Dashboard: ClaimUI claim ref num: amount: status: xxxxxxx $100 submitted yyyyyyy $50 approved zzzzzzzz $20 paid Fore more details look into the HeliusHCMRequirements.doc | Shekhar |  | Meeting on 13-06-2018 | Not started | Not started | Not started | Not started
55 | 2018-06-14 | Functionality | HR dashboard | Claims | HR dash board: ClaimUI Empname : claim ref num: amount: status: emp1 xxxxxxx $100 submitted emp2 yyyyyyy $50 approved emp3 zzzzzzzz $20 paid. Fore more details look into the HeliusHCMRequirements.doc | Shekhar |  | Meeting on 13-06-2018 | Not started | Not started | Not started | Not started
56 | 2018-06-14 | Functionality | Employee Feedback | Feedback | Feedback: Day 1------------ Day7 ----------Day90--------Day180----Day270 Criteria to select employee 7 days 7 days template 30 days 30 days template 90 days 90 days template 180 days 180 days template 270 days 270 days template | Shekhar |  | Meeting on 14-06-2018 | Not started | Not started | Not started | Not started
57 | 2018-06-14 | Functionality | Employee Master | Employee Create section | * As part of in boarding checklist * generate employee id. Number starting with 3000 onwards | Shekhar |  | Meeting on 14-06-2018 | Not started | Not started | Not started | Not started
58 | 2018-06-26 | Functionality | User access management | User access management | For details of user management, look into the HeliusHCMRequirements.doc | Tirumala and Team |  |  | Not started | Not started | Not started | Not started
59 | 2018-06-26 | Functionality | Employee dashboard | Employee dashboard for request for letters from HR | Employee Request management : There will be place in the employee dash board where employee can raise a request for these letters. Letter format and other request guidelines will be available in this place in the form of link. There will be a request button using which employee can submit the request form in the correct format. These request details will be captured in the system and the request will be populated in “HR dashboard for employee requests” for HR actions. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
60 | 2018-06-26 | TechnicalPOC | Employee dashboard | Employee dashboard for request for letters from HR | Employees make various type of requests to HR. The entire process of this request management need to ve automated with the help of third party tools or build from scratch. Bot the options will be evaluated. For more details look into the HeliusHCMRequirements.doc The screen shots related to this are provided in the ppt. | Tirumala and Team |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
61 | 2018-06-26 | Functionality | HR dashboard | HRTimesheet dashboard | Time Sheet management: Time sheet requirement details are given in HeliusHCMRequirements.doc HR time sheet dash board and Employee dash board for UI screen shots for timesheets in the attached ppt. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
62 | 2018-06-26 | Functionality | Employee dashboard | Employee dashboard | Employee dashborard will an option for employee to download manual timesheet template, fill it, rename it as per the naming convention and upload the filled timesheet to system.Time sheet requirement details are given in HeliusHCMRequirements.doc HR time sheet dash board and Employee dash board for UI screen shots for timesheets in the attached ppt. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
63 | 26.06.2018 | Functionality | HR dashboard | HR dashboard for employee requests | An HR person, in this dash board can assign this request to himself/herself or whoever is the right HR person to act on this request. During the processing of this request processing, HR persons can reassign the request to other HR persons or reassign back to employee for any other information. On successful completion of the request, it moves to “closed” state. The screen shots related to this are provided in the ppt. For more details look into the HeliusHCMRequirements.doc. For more details look in payslips section in HeliusHCMRequirements.doc | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
64 | 26.06.2018 | Functionality | Employee dashboard | Employee Feedback | Employee feedback is obtained from an employee at different time intervals from the day of joining. Feedback is sought on 7th,30th, 90th,180th 270th day of the employee after he joins. Need to explore whether any third party survey tools like survey monkey can be integrated to our system for this purpose instead of building from scratch For more details look in employee feedback section in HeliusHCMRequirements.doc | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
65 | 26.06.2018 | TechnicalPOC | SMS | SMS gateway | SMS to employees is a generic feature which is used across the app wherever required. Example: updating the timesheet status, payslip status etc.. Need to explore the integration of our system with SMS gateway. Need to evualuate the cost involved. For more details look into the HeliusHCMRequirements.doc | Tirumala and Team |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
66 | 26.06.2019 | Functionality | Audit trail | Audit trail | All the CRUD operations of the users in the app need to be captured in the system. Need to work on how these audit trail details made visible to the users with appropriate privileges. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
67 | 26.06.2019 | TechnicalPOC | Cloud | Cloud deployment | Deployment of the app package into AWS. | Tirumala and Team |  |  | Not started | Not started | Not started | Not started
68 | 26.06.2019 | Functionality | Employee dashboard | Employee Appraisals | Employee appraisals are an important part of an employee journey Dates “Appraisal due on ” and “Merit increase from” will be published in employee dash board. Entire appraisal workflow is not in the scope of the current work. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
69 | 26.06.2019 | Functionality |  | Employee Professional details | There should 4 to 5 key words related to employee skills need to be captured in professional details section. These key words will be useful for HR and recruiters during recruitment | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
70 | 26.06.2019 | Functionality | Employee master | Employee Personal Details | There should be aplace in the app to capture the hobbies of the employees. This enables employees of similar hobbies to connect to each other | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
71 | 26.06.2019 | TechnicalPOC | Firewall | Firewall issues | Need to know about client firewall issues, if any, which may prevent Helius employees to access the app from the client network | Tirumala and Team |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
72 | 29.06.2019 | Functionality | Historical data | employee leaves | Existing employee data should be uploaded into the system before employees start using the system. Based on this data only, employee leaves will be shown in the emloyee dashboard. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
73 | 29.06.2019 | Functionality | Historical data | employee paylsips | Atleast, three past month employee payslips should be loaded into the system nad make them for employees for download in employee dashboard when the system goes live | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started
74 | 29.06.2019 | Functionality | Historical data | employee records | All the existing employee records must be uploaded into the system. Once the data is available. Employee and/or HR can update this data via the app as required. | Shekhar |  | Discussions from 14th to 26th June 2018 | Not started | Not started | Not started | Not started

## Phase1-HR-EmployeeJourney
Employee Action Journey | Sidebar menuitem | HR timesheet dashboard | HR employee dashboard for requests
Creating an offer | Create in employee master
Creation of new employee | Create in employee master | No | No
maintain onboarding documents | Checklist UI for capturing the documents and stroring in DB | No | No
Maintain employee master record | Update in employee master | No | No
Update timesheets | yes | yes | no
Update leaves | UI to update leaves for employees | no | no
Maintain claims | yes | yes | no
Maintain apprisal records ( not needed) | yes | no | no
Apply merit increase | yes | no | no
Exit employee | UI to set resignation date and last date. | no | no
Convert employee to client(special case of exit) | Exit employee | no | no

## Phase2-Employeedashboard
Employee related features | Employee dash board
Leaves details | Leaves section
Downloading manual timesheet and uploading filled timesheet | timesheets section
Personal details | view and update personal details
Claims details and uploading new claims | Claims section
Downloading Payslips | Payslips section
Sending letter requests | Request for letters from HR
Client details | Client details
HR touch points | HR touch points section