## Alltasks
TOTAL TASKS
Task | Category | Assigned To
HR timesheet bashboard UI | HR timesheet dash board | Umesh
Employee dash board UI | Employee dash board | Umesh
capturing RTS timehseet submitted by HR and sending to backend in json format | RTS timesheet | Umesh
captruring manual timehseet submitted by employee and sending to backend in json format | Manual timesheets | Umesh
Popup to show the details of RTS report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh
Pop to show the details of manual timesheet report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh
REST service to process json request for RTS timesheet | RTS timesheet | Vinay
Validations of RTS timessheet for correct and wrong clockers and sending back result to front end | RTS timesheet | Vinay
sending SMS regarding the timesheet status to employees | RTS timesheet | Vinay
Saving the RTS timesheet details into DB | RTS timesheet | Vinay
Saving the manual timesheet details into DB | Manual timesheets | Vinay
Creation of timesheet DB schema | Manual timesheets | Rajesh
Batch job to change the manual timesheet status from received to unprocessed every day night at 12:00 pm | Manual timesheets | Rajesh
End to end integration | RTS timesheet | Entire Team
End to end integration | Manual timesheets | Entire Team
Employee timesheet status query dashboard UI and displaying search results | Manual timesheets | Umesh
REST service to service the search query for employee timesheet status query | Manual timesheets | Vinay
Deployment of RTS timesheets feature in AWS | RTS timesheet | Tirumala and Rajesh
Deployment of manual timesheets feature in AWS | Manual timesheets | Tirumala and Rajesh
Creation of employee leaves DB schema | Leaves | Rajesh
Gathering leave records data for the current year from HR in the predetermined format | Leaves | Rajesh
Batch job to load the leave history to DB | Leaves | Rajesh
Getting employee leave details from back end and displaying in employee dashboard | Leaves | Umesh
Processing employee leave details from RTS timesheet and updating DB | Leaves | Vinay
UI to submit employee leave record in HR timesheet dashboard for manual timesheet employees | Leaves | Umesh
Cpatruing employee leave record updated by HR from HR timesheet dashboard for manual timesheet employees and sending in JSON format to baackend | Leaves | Umesh
REST service to process the employee leave record for manual timesheet employees | Leaves | Vinay
REST service tofecth the employee leave record from DB and sendig to front end in json format | Leaves | Vinay
Fetching leave history from backend and displaying in employee dashboard | Leaves | Umesh
End to end integration | Leaves | Entire Team
Deployment of leaves feature in AWS | Leaves | Tirumala and Rajesh
Creation of employee requests DB schema | Employee requests | Rajesh
HR dashboard for employee requests UI | Employee requests | Umesh
New employee request UI | Employee requests | Umesh
Capturing the new employee request details and submitting to backend in JSON format | Employee requests | Umesh
REST service to process the new employee request and updating the DB | Employee requests | Vinay
Fetching th employee request processing activity from backend and displayed weekly activity dashboard | Employee requests | Umesh
REST service to process the request for weekly activity dash board | Employee requests | Vinay
Fetching the data for internal HR actions dashboard from end and displaying dashboard | Employee requests | Umesh
REST service to process the request for internal HR actions dashboard | Employee requests | Vinay
Capturing the request status change in dashboard by HR and sending to backend in JSON format | Employee requests | Umesh
REST service to process the request status and save in DB | Employee requests | Vinay
End to end integration | Employee requests | Entire Team
Deployment of requests feature in AWS | Employee requests | Tirumala and Rajesh
popup to show UI to upload new claim from employee dashboard | Claims | Umesh
Capture the new clai details from claim UI and send to backend for saving into DB | Claims | Umesh
REST service to process the new claim request from employee dashboard | Claims | Vinay
Fetching the claim history data from back end and displaying cliams section of employee dashboard | Claims | Umesh
Sending SMS to employee regarding their claim status | Claims | Vinay
Deployment of claims feature in AWS | Employee requests | Tirumala and Rajesh
Changing the employee creation UI with new changes(professional details and other changes in other sections) | EmployeeMaster | Umesh
Capturing the employee details and sending to backend in JSON format | EmployeeMaster | Umesh
Updating REST service to process the new employee details from employee master create section and save in DB | EmployeeMaster | Vinay
Updating the existing emplaoyee DB schema as per the new changes in employee creation | EmployeeMaster | Rajesh
updating the existing exmployee records in DB as per the new schema | EmployeeMaster | Rajesh
Client master DB schema | Client Master | Rajesh
Client master UI for creating clients | Client Master | Umesh
Capturing client master details from create UI and sending to backend in JSON format | Client Master | Umesh
REST service to process and save the new client details in client DB | Client Master | Vinay
client serach UI for viewing and updating exiting client in client master | Client Master | Umesh
REST service to process client search query and send response in JSON format | Client Master | Vinay
Deployment of cleint master feature in AWS | Client Master | Tirumala and Rajesh
Creation of new user UI | User access management | Umesh
Capturing new user details and sending to back end in JSON fromat | User access management | Umesh
REST service to process new user request from front end and save in DB | User access management | Vinay
UI to add new roles to a user | User access management | Umesh
Capturing new role details for a user and sending to backend in JSOn format | User access management | Umesh
REST service to process roles addition/updation request from front end and save in DB | User access management | Vinay
Setting permissions to each role (no UI required as of now) | User access management | Umesh
Cloud deployment | Cloud | Tirumala
SMS gateway integration | SMS gateway | Tirumala
Firewall issues | common | Tirumala
Creation of DB schema for payslips | Payslips | Rajesh
Loading three months payslips for preceding months | Payslips | Rajesh
Batchjob to load payslips for every month into DB | Payslips | Rajesh and Vinay
downloading the payslip from backend from employee dash board | Payslips | Umesh
REST service to process payslip downloading request | Payslips | Vinay
End to end integration | Payslips | Entire Team
Deployment of paylips feature in AWS | Payslips | Tirumala and Rajesh
Creation of DB schema for audit trail | Audit trail | Rajesh
Creation of UI to show audit history in app | Audit trail | Umesh
updating the create, update actions into audit trail table | Audit trail | Vinay
Fetching audit history from backend to diaply in audit trail UI | Audit trail | Umesh
REST service to process audit history request and send response in json format | Audit trail | Vinay
End to end integration | Audit trail | Tirumala and Rajesh
Deployment of audit trail in AWS | Audit trail | Entire Team
popup to show employee personal details in employee dashboard for view and update | EmployeeMaster | Umesh
Capturing any updated details in personal information by employee in employee dash board and sending the updated information to backend in json format | EmployeeMaster | Umesh
REST service to update the changes into DB | EmployeeMaster | Vinay
Popup to show HR touch points in employee dashboard | EmployeeMaster | Umesh
Cloud deployment | common | Tirumala
SMS gateway integration | common | Tirumala
Firewall issues | common | Tirumala

## Total estimate
Feature | Development |  | 1st round testing |  | 1st round bug fixing |  | 2nd round testing |  | 2nd round bug fixing |  | Final round testing(end users) |  | Exit criteria | Final delivery date
| start date | end date | start date | end date | start date | end date | start date | end date | start date | end date | start date | end date
RTS timesheet | 2018-07-09 | 2018-07-20 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-27 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-03 | end user signoff | 2018-08-06
Manual timesheet | 2018-07-23 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-16 | 2018-08-17 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | end user signoff | 2018-08-24
Common | 2018-07-23: 2018-07-09; 2018-08-08: 2018-07-31 | shekhar sign off
Leaves | 2018-08-06 | 2018-08-17 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-08-31 | end user signoff | 2018-09-04
Useraccess management | 2018-07-16 | 2018-07-27 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-16 | 2018-08-17 | 2018-08-18 | end user signoff | 2018-08-24
Employee Requests | 2018-08-18 | 2018-08-31 | 2018-09-03 | 2018-09-05 | 2018-09-06 | 2018-09-07 | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-14 | 2018-09-17 | 2018-09-18 | end user signoff | 2018-09-21
Claims | 2018-09-03 | 2018-09-11 | 2018-09-12 | 2018-09-14 | 2018-09-15 | 2018-09-16 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-25 | 2018-09-26 | 2018-09-27 | end user signoff | 2018-09-28
Employee master | 2018-09-12 | 2018-09-26 | 2018-09-28 | 2019-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-15 | end user signoff | 2018-10-16
Client master | 2018-09-27 | 2018-10-12 | 2018-10-15 | 2018-10-17 | 2018-10-19 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-29 | 2018-10-30 | end user signoff | 2018-10-31
Payslips | 2018-10-15 | 2018-10-22 | 2018-10-25 | 2018-10-26 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-05 | 2018-11-06 | 2018-11-07 | end user signoff | 2018-11-09
Audit trail | 2018-10-23 | 2018-11-05 | 2018-11-08 | 2018-11-09 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-19 | 2018-11-20 | 2018-11-21 | end user signoff | 2018-11-23
| Final delivery date | 2018-11-23
Phase I estimate
Feature | 2018-10-23: Development; 2018-11-08: 1st round testing; 2018-11-12: 1st round bug fixing; 2018-11-14: 2nd round testing; 2018-11-16: 2nd round bug fixing; 2018-11-20: Final round testing(end users) | Exit criteria | Final delivery date
Employee master | 2018-07-11 | 2018-07-25 | 2018-07-26 | 2019-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-10-09 | end user signoff | 2018-08-10
onboarding documents | 2018-07-26 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-14 | 2018-08-16 | 2018-08-17 | end user signoff | 2018-08-17
ExitEmployee | 2018-08-06 | 2018-08-10 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | end user signoff | 2018-08-31
Clientmaster | 2018-07-11 | 2018-07-27 | 2018-07-31 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-17 | end user signoff | 2018-08-24
RTS timesheet | 2018-08-13 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-09-03 | 2018-09-04 | end user signoff | 2018-09-14
Manual timesheet | 2018-08-21 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-08 | 2018-09-09 | 2018-09-10 | end user signoff | 2018-09-14
Leaves | 2018-08-30 | 2018-09-14 | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-10-01 | end user signoff | 2018-10-01
Claims | 2018-08-30 | 2018-09-14 | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-10-01 | end user signoff | 2018-10-05
ApplyMeritincrease | 2018-09-17 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-10-01 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | end user signoff | 2018-10-12
| Final delivery date | 2018-10-05
Feature | 2018-09-17: Outcome; 2018-09-26: Delivery date
Employee master | 2018-09-17: 1.Entry of new offer into the system 2.Creation of employee record after employee accepts offer. If employee rejects offer, can make the offer inactive in the system 3. Ability to enter erms and conditions, employee personal details, workpermit details, assignment details, leave details, salary details 4. Migrate the existing employees data will be into the system and be vailable for updation; 2018-09-26: 2018-08-10
onboarding documents | 2018-09-17: 1. Ability to upload required employee specific onboarding documents.; 2018-09-26: 2018-08-17
ExitEmployee | 2018-09-17: 1. Create employee checklist 2. Abiity to monitor the exit process using exit checklist. 3 System handles special scenario of employee conversion to client; 2018-09-26: 2018-08-31
Clientmaster | 2018-09-17: 1. Adding new client details into system 2. Updating the existing client details 3. Exisitng client data will be uploaded and be available for updation; 2018-09-26: 2018-08-24
RTS timesheet | 2018-09-17: 1. Process HR uploaded RTS timesheet for validation errors 2. downloads the correct and wrong clockers excels after processing the timesheet 3. send email notification to employee on timesheet status 3. Save the RTS timesheet and each employee timesheet status in the system 4. HR will be able to see in HR timesheet dashboard the timesheet statistics related to RTS timesheet report; 2018-09-26: 2018-09-14
Manual timesheet | 2018-09-17: 1. downloads latest timesheets from timesheets@helius-tech.com when triggered by HR 2. saves the timesheet in the system. 3. Parses the timesheet for any errors. Updates the timesheet status in the system 4. HR will be able to see in HR timesheet dashboard the timesheet statistics related to manual timesheets 5. upload the manual timesheet template; 2018-09-26: 2018-09-14
Leaves | 2018-09-17: 1. Scans the leaves from both RTS timesheet and manual timesheet for leaves availed. Updates the system with leave date of the employee 2. Provides the ability to enter employee specific leave data manually by HR in case of special situations 3. leave elibility and utilization data of the employees for the current year will be gathered and uploaded into system one week before feature goes live; 2018-09-26: 2018-10-01
Claims | 2018-09-17: 1. HR will be able to enter new claims and change the status(submitted, incomplete, partially reimbursed, completely reimbursed etc..) as the claim goes through its processing. 2. All the active employee claims data in the current year will be gathered and uploaded into system one week before system goes live; 2018-09-26: 2018-10-05
ApplyMeritincrease | 2018-09-17: 1. HR can enter and save the merit increase details in the system after an employee appraisal like merit increase %, new CTC, effective from date etc..; 2018-09-26: 2018-10-12

## Phase1-HR-Employeejourney
HR-Employee Journey
| Task | Category | Assigned To | Estimate (in days)
| Creation of employee master UI to capture new employee data | employee master | Umesh | 1
| Capture the new employee data from UI, prepare json and send to backend | employee master | Umesh | 2
| UI to search and display existing employee data and also ability to update employee information. | employee master | Umesh | 2
| Checklist UI for capturing the onboarding documents and stroring in DB | onboarding documents | Umesh | 2
| DB schema for employee master | employee master | Rajesh | 1
| REST service to create new employee in DB | employee master | Vinay | 1
| REST service to update an existing employee into DB | employee master | Vinay | 2
| End to end integration | employee master | Umesh and Vinay | 2
| Gathering existing employee data from HR | employee master | Rajesh | 7
| Script for loading existing employee data into DB | employee master | Rajesh | 3
| Deploying employee master feature into AWS | employee master | Tirumala and Rajesh | 1
| UI to upload RTS timesheet | Timesheets | Umesh | 1
| REST service to capture and perform validations on RTS timesheet and send response back to front dnd | Timesheets | Vinay | 2
| Displaying the RTS timesheet validation result to HR and also save result excel | Timesheets | Umesh | 2
| Update in DB the RTS timeheet status of each employee | Timesheets | Vinay | 2
| UI to trigger a job to check timesheets inbox in email server and receive latest timesheets | Timesheets | Umesh | 1
| REST service job to check timesheets inbox in email server and receive latest timesheets | Timesheets | Vinay | 3
| REST service to perform validations on manual timesheets | Timesheets | Vinay | 3
| Update in DB the manual timeheet status of each employee | Timesheets | Vinay | 2
| Gathering leaves data for existing employees from HR | Leaves | Rajesh | 14
| Script to upload leaves data for existing employees into DB | Leaves | Rajesh | 2
| UI to update leave record of an employee | Leaves | Umesh | 1
| Capture the leave records in JSON format and send to backend | Leaves | Umesh | 1
| REST service to receive leave record json, perform validations, save in DB | Leaves | Vinay | 2
| Extract leaves from RTS timesheet and update in DB | Leaves | Vinay | 2
| Extract leaves from manual timesheet and update in DB | Leaves | Vinay | 2
| End to end integration | Leaves | Umesh and Vinay | 2
| Deploying leaves feature into AWS | Leaves | Tirumala and Rajesh | 1
| Gathering claims data for existing employees from HR | Claims | Rajesh | 10
| Script to upload claims data for existing employees into DB | Claims | Rajesh | 2
| UI to update claim record of an employee | Claims | Umesh | 1
| Capture the claim record in JSON format and send to backend | Claims | Umesh | 2
| REST service to receive claim record json, perform validations, save in DB | Claims | Vinay | 2
` | End to end integration | Claims | Umesh and Vinay | 2
| Deploying claims feature into AWS | Claims | Tirumala and Rajesh | 1
| UI to upload employee appraisal data into DB | Appraisal | Umesh
| Capture the appraisal record in JSON format and send to backend | Appraisal | Umesh
| REST service to receive appraisal record json and save in DB | Appraisal | Vinay
| Deploying Appraisal feature into AWS | Appraisal | Tirumala and Rajesh
| UI to upload employee merit increase data into DB | Merit increase | Umesh | 2
| Capture the merit increase record in JSON format and send to backend | Merit increase | Umesh | 2
| REST service to receive merit increase record json and save in DB | Merit increase | Vinay | 2
| End to end integration | Merit increase | Entire team | 2
| Deploying merit increase feature into AWS | Merit increase | Tirumala and Rajesh | 2
` | Convert employee to client | employee master | Umesh and Vinay | 1
| UI to set resignation date and last date. | Exit employee | Umesh | 1
| REST service to capture exit dates record json and save in DB | Exit employee | Vinay | 2
| UI to capture employee exit checklist | Exit employee | Umesh | 2
| REST service to get employee exit documents in json and save in DB | Exit employee | Vinay | 2
` | End to end integration | Exit employee | Umesh and Vinay | 2
| Deploying exit employee feature into AWS | Exit employee | Tirumala and Rajesh | 1
| Creation of DB schema | User access management | Rajesh | 2
| Creation of new user UI | User access management | Umesh | 1
| Capturing new user details and sending to back end in JSON fromat | User access management | Tirumala | 1
| REST service to process new user request from front end and save in DB | User access management | Tirumala | 1
| UI to add new roles to a user | User access management | Umesh | 1
| Capturing new role details for a user and sending to backend in JSOn format | User access management | Tirumala | 1
| REST service to process roles addition/updation request from front end and save in DB | User access management | Tirumala | 1
| Setting permissions to each role (no UI required as of now) | User access management | Tirumala | 2
| End to end integration | User access management | Entire team | 2
| DB schema for client master | Clientmaster | Rajesh | 2
| Gathering existing clients details from HR | Clientmaster | Rajesh | 7
| Script for loading existing client data into DB | Clientmaster | Rajesh | 2
| Creation of client master UI to enter client details | Clientmaster | Umesh | 2
| Capturing the client details and send to backend in JSON form | Clientmaster | Tirumala | 2
| REST service to receive the client json data and save it in DB | Clientmaster | Tirumala | 2
| UI for searching, displaying and updating the client details | Clientmaster | Umesh | 2
| REST service to receive the updated client json data and save it in DB | Clientmaster | Tirumala | 2
| End to end integration | Clientmaster | Entire team | 2

## timesheets
Time sheet tasks
Task | Category | Assigned To | Estimate (in days)
HR timesheet dashboard UI (static) | HR timesheet dash board | Umesh | 2
Employee dash board UI (static) | Employee dash board | Umesh | 1
capturing RTS timehseet submitted by HR and sending to backend in json format | RTS timesheet | Umesh | 1
Finalizing manual timesheet template | Manual timesheets | Entire Team | 2
capturing manual timehseet submitted by employee and sending to backend in json format | Manual timesheets | Umesh | 1
Popup to show the details of RTS report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh | 3
Pop to show the details of manual timesheet report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh | 2
REST service to process json request for RTS timesheet | RTS timesheet | Vinay | 2
Validations of RTS timessheet for correct and wrong clockers and sending back result to front end | RTS timesheet | Vinay | 2
sending SMS regarding the timesheet status to employees | RTS timesheet | Vinay | 2
Saving the RTS timesheet details into DB | RTS timesheet | Vinay | 2
Saving the manual timesheet details into DB | Manual timesheets | Vinay | 2
Creation of timesheet DB schema | Manual timesheets | Rajesh | 1
Batch job to change the manual timesheet status from received to unprocessed every day night at 12:00 pm | Manual timesheets | Rajesh | 1
End to end integration | RTS timesheet | Entire Team | 2
Employee timesheet status query dashboard UI and displaying search results | Manual timesheets | Umesh | 2
REST service to service the search query for employee timesheet status query | Manual timesheets | Vinay | 2
Deployment of RTS timesheets feature in AWS | RTS timesheet | Tirumala and Rajesh | 1
End to end integration | Manual timesheets | Entire Team | 2
Deployment of manual timesheets feature in AWS | Manual timesheets | Tirumala and Rajesh | 1
SMS gateway integration | SMS gateway | Tirumala | 2
RTS timesheet
Start date = 09-07-2018
End date = 06-08-2018
Manual timesheet
Start date = 23-07-2018
End date = 24-08-2018

## Leaves
LEAVES
Task | Category | Assigned To | Estimate (in days)
Creation of employee leaves DB schema | Leaves | Rajesh | 1
Gathering leave records data for the current year from HR in the predetermined format | Leaves | Rajesh | 5
Batch job to load the leave history to DB | Leaves | Rajesh | 2
Getting employee leave details from back end and displaying in employee dashboard | Leaves | Umesh | 2
REST service to process employee leave details from RTS timesheet and updating DB | Leaves | Vinay | 2
UI to submit employee leave record in HR timesheet dashboard for manual timesheet employees | Leaves | Umesh | 1
Capturing employee leave record updated by HR from HR timesheet dashboard for manual timesheet employees and sending in JSON format to backend | Leaves | Umesh | 1
REST service to fecth the employee leave records from DB and sendig to front end in json format | Leaves | Vinay | 2
Fetching leave history from backend and displaying in employee dashboard | Leaves | Umesh | 2
End to end integration | Leaves | Entire Team | 2
Deployment of leaves feature in AWS | Leaves | Tirumala and Rajesh | 1
LEAVES
Start date = 06-08-2018
End date = 04-09-2018

## Useraccess management
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema | User access management | Rajesh | 2
Creation of new user UI | User access management | Umesh | 1
Capturing new user details and sending to back end in JSON fromat | User access management | Tirumala | 1
REST service to process new user request from front end and save in DB | User access management | Tirumala | 1
UI to add new roles to a user | User access management | Umesh | 1
Capturing new role details for a user and sending to backend in JSOn format | User access management | Tirumala | 1
REST service to process roles addition/updation request from front end and save in DB | User access management | Tirumala | 1
Setting permissions to each role (no UI required as of now) | User access management | Tirumala | 2
End to end integration | User access management | Entire team | 2
start date: 16-07-2018
end date : 24-08-2018

## Employee Requests
Employee Requests
Task | Category | Assigned To | Estimate (in days)
Creation of employee requests DB schema | Employee requests | Rajesh | 1
New employee request UI | Employee requests | Umesh | 1
Capturing the new employee request details and submitting to backend in JSON format | Employee requests | Umesh | 1
REST service to process the new employee request and updating the DB | Employee requests | Vinay | 1
Fetching the employee request processing activity from backend and displayed weekly activity dashboard | Employee requests | Umesh | 1
REST service to process the request for weekly activity dash board | Employee requests | Vinay | 2
Fetching the data for internal HR actions dashboard from back end and displaying dashboard | Employee requests | Umesh | 1
REST service to process the request for internal HR actions dashboard | Employee requests | Vinay | 1
Capturing the request status change in dashboard by HR and sending to backend in JSON format | Employee requests | Umesh | 1
REST service to process the request status and save in DB | Employee requests | Vinay | 2
End to end integration | Employee requests | Entire Team | 2
Deployment of requests feature in AWS | Employee requests | Tirumala and Rajesh | 1
Start date = 18-08-2018
end date = 21-09-2018

## Claims
Task | Category | Assigned To | Estimate (in days)
Creation of claims DB schema | Claims | Rajesh | 1
popup to show UI to upload new claim from employee dashboard | Claims | Umesh | 1
Capture the new claim details from claim UI and send to backend for saving into DB | Claims | Umesh | 1
REST service to process the new claim request from employee dashboard | Claims | Vinay | 2
Fetching the claim history data from back end and displaying cliams section of employee dashboard | Claims | Umesh | 2
Sending SMS to employee regarding their claim status | Claims | Vinay | 1
End to end integration | Claims | Entire team | 2
Deployment of claims feature in AWS | Claims | Tirumala and Rajesh | 1
Start date = 03-09-2018
End date = 28-09-02018

## Employeemaster
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Changing the employee creation UI with new changes(professional details and other changes in other sections) | EmployeeMaster | Umesh | 1
Capturing the employee details and sending to backend in JSON format | EmployeeMaster | Umesh | 2
Updating REST service to process the new employee details from employee master create section and save in DB | EmployeeMaster | Vinay | 2
Updating the existing employee DB schema as per the new changes in employee creation | EmployeeMaster | Rajesh | 1
updating the existing exmployee records in DB as per the new schema | EmployeeMaster | Rajesh | 7
end to end integration | EmployeeMaster | Entire team | 2
popup to show employee personal details in employee dashboard for view and update | EmployeeMaster | Umesh | 2
Capturing any updated details in personal information by employee in employee dash board and sending the updated information to backend in json format | EmployeeMaster | Umesh | 1
REST service to update the changes into DB | EmployeeMaster | Vinay | 1
Popup to show HR touch points in employee dashboard | EmployeeMaster | Umesh | 1
start date = 12-09-2018
end date = 16-10-2018
* Rajesh will start collecting the data from much earlier.

## Client Master
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Client master DB schema | Client Master | Rajesh | 2
Client master UI for creating clients | Client Master | Umesh | 3
Capturing client master details from create UI and sending to backend in JSON format | Client Master | Umesh | 2
REST service to process and save the new client details in client DB | Client Master | Vinay | 2
client search UI for viewing and updating exiting client in client master | Client Master | Umesh | 2
REST service to process client search query and send response in JSON format | Client Master | Vinay | 2
End to end integration | Client Master | Entire team | 2
Deployment of client master feature in AWS | Client Master | Tirumala and Rajesh | 1
start date = 27-09-2018
end date = 31-10-2018

## Payslips
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema for payslips | Payslips | Rajesh | 1
Loading three months payslips for preceding months | Payslips | Rajesh | 2
Batchjob to load payslips for every month into DB | Payslips | Rajesh and Vinay | 1
downloading the payslip from backend from employee dash board | Payslips | Umesh | 2
REST service to process payslip downloading request | Payslips | Vinay | 2
End to end integration | Payslips | Entire Team | 1
Deployment of paylips feature in AWS | Payslips | Tirumala and Rajesh | 1
start date = 15-10-2018
end date = 09-11-2018

## Audittrail
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema for audit trail | Audit trail | Rajesh | 1
Creation of UI to show audit history in app | Audit trail | Umesh | 1
Updating the create, update actions into audit trail table | Audit trail | Vinay | 2
Fetching audit history from backend to display in audit trail UI | Audit trail | Umesh | 2
REST service to process audit history request and send response in json format | Audit trail | Vinay | 2
End to end integration | Audit trail | Tirumala and Rajesh | 1
Deployment of audit trail in AWS | Audit trail | Entire Team | 1
start date 23-10-2018
end date = 23-11-2018

## common
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Cloud deployment | common | Tirumala | 7
SMS gateway integration | common | Tirumala | 7
Firewall issues | common | Tirumala | 7
start date | 2018-07-09
end date | 2018-07-31

## Risks
Risks | Type of Risk | Description | Mitigation
SMS gateway not working | Technical | if SMS gateway fails, app can not send the SMS regarding the timesheet status or request status to employees | Need to see whether we can fall back on secondary SMS gateway at runtime.
Wildfly server (backend) fails or slows down | Technical | After continuously running for days together, wildfly server may run of memory or slowsdown. | Need to closely monitor the server status on a daily basis.
Firewall issues | Technical | whenever an update done to firewall at the client, our app might get blocked. | Need to closely engage with client network team so that we will get information sooner than later in case of any firewall changes
DB backup fails | Technical | DB backups are scheduled every day and it happens automatically | DBA should monitor the DB backups tasks closely and make sure that he is notified immediately whenever any backup fails
App team member is absent | non-technical | team member onleave for more days on health grounds, family emergency etc.. | cross team learning might help. But, in a small team, where everybody is busy with their work, is this feasible?