## Alltasks
TOTAL TASKS
Task | Category | Assigned To
HR timesheet bashboard UI | HR timesheet dash board | Umesh
Employee dash board UI | Employee dash board | Umesh
capturing RTS timehseet submitted by HR and sending to backend in json format | RTS timesheet | Umesh
captruring manual timehseet submitted by employee and sending to backend in json format | Manual timesheets | Umesh
Popup to show the details of RTS report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh
Pop to show the details of manual timesheet report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh
REST service to process json request for RTS timesheet | RTS timesheet | Vinay
Validations of RTS timessheet for correct and wrong clockers and sending back result to front end | RTS timesheet | Vinay
sending SMS regarding the timesheet status to employees | RTS timesheet | Vinay
Saving the RTS timesheet details into DB | RTS timesheet | Vinay
Saving the manual timesheet details into DB | Manual timesheets | Vinay
Creation of timesheet DB schema | Manual timesheets | Rajesh
Batch job to change the manual timesheet status from received to unprocessed every day night at 12:00 pm | Manual timesheets | Rajesh
End to end integration | RTS timesheet | Entire Team
End to end integration | Manual timesheets | Entire Team
Employee timesheet status query dashboard UI and displaying search results | Manual timesheets | Umesh
REST service to service the search query for employee timesheet status query | Manual timesheets | Vinay
Deployment of RTS timesheets feature in AWS | RTS timesheet | Tirumala and Rajesh
Deployment of manual timesheets feature in AWS | Manual timesheets | Tirumala and Rajesh
Creation of employee leaves DB schema | Leaves | Rajesh
Gathering leave records data for the current year from HR in the predetermined format | Leaves | Rajesh
Batch job to load the leave history to DB | Leaves | Rajesh
Getting employee leave details from back end and displaying in employee dashboard | Leaves | Umesh
Processing employee leave details from RTS timesheet and updating DB | Leaves | Vinay
UI to submit employee leave record in HR timesheet dashboard for manual timesheet employees | Leaves | Umesh
Cpatruing employee leave record updated by HR from HR timesheet dashboard for manual timesheet employees and sending in JSON format to baackend | Leaves | Umesh
REST service to process the employee leave record for manual timesheet employees | Leaves | Vinay
REST service tofecth the employee leave record from DB and sendig to front end in json format | Leaves | Vinay
Fetching leave history from backend and displaying in employee dashboard | Leaves | Umesh
End to end integration | Leaves | Entire Team
Deployment of leaves feature in AWS | Leaves | Tirumala and Rajesh
Creation of employee requests DB schema | Employee requests | Rajesh
HR dashboard for employee requests UI | Employee requests | Umesh
New employee request UI | Employee requests | Umesh
Capturing the new employee request details and submitting to backend in JSON format | Employee requests | Umesh
REST service to process the new employee request and updating the DB | Employee requests | Vinay
Fetching th employee request processing activity from backend and displayed weekly activity dashboard | Employee requests | Umesh
REST service to process the request for weekly activity dash board | Employee requests | Vinay
Fetching the data for internal HR actions dashboard from end and displaying dashboard | Employee requests | Umesh
REST service to process the request for internal HR actions dashboard | Employee requests | Vinay
Capturing the request status change in dashboard by HR and sending to backend in JSON format | Employee requests | Umesh
REST service to process the request status and save in DB | Employee requests | Vinay
End to end integration | Employee requests | Entire Team
Deployment of requests feature in AWS | Employee requests | Tirumala and Rajesh
popup to show UI to upload new claim from employee dashboard | Claims | Umesh
Capture the new clai details from claim UI and send to backend for saving into DB | Claims | Umesh
REST service to process the new claim request from employee dashboard | Claims | Vinay
Fetching the claim history data from back end and displaying cliams section of employee dashboard | Claims | Umesh
Sending SMS to employee regarding their claim status | Claims | Vinay
Deployment of claims feature in AWS | Employee requests | Tirumala and Rajesh
Changing the employee creation UI with new changes(professional details and other changes in other sections) | EmployeeMaster | Umesh
Capturing the employee details and sending to backend in JSON format | EmployeeMaster | Umesh
Updating REST service to process the new employee details from employee master create section and save in DB | EmployeeMaster | Vinay
Updating the existing emplaoyee DB schema as per the new changes in employee creation | EmployeeMaster | Rajesh
updating the existing exmployee records in DB as per the new schema | EmployeeMaster | Rajesh
Client master DB schema | Client Master | Rajesh
Client master UI for creating clients | Client Master | Umesh
Capturing client master details from create UI and sending to backend in JSON format | Client Master | Umesh
REST service to process and save the new client details in client DB | Client Master | Vinay
client serach UI for viewing and updating exiting client in client master | Client Master | Umesh
REST service to process client search query and send response in JSON format | Client Master | Vinay
Deployment of cleint master feature in AWS | Client Master | Tirumala and Rajesh
Creation of new user UI | User access management | Umesh
Capturing new user details and sending to back end in JSON fromat | User access management | Umesh
REST service to process new user request from front end and save in DB | User access management | Vinay
UI to add new roles to a user | User access management | Umesh
Capturing new role details for a user and sending to backend in JSOn format | User access management | Umesh
REST service to process roles addition/updation request from front end and save in DB | User access management | Vinay
Setting permissions to each role (no UI required as of now) | User access management | Umesh
Cloud deployment | Cloud | Tirumala
SMS gateway integration | SMS gateway | Tirumala
Firewall issues | common | Tirumala
Creation of DB schema for payslips | Payslips | Rajesh
Loading three months payslips for preceding months | Payslips | Rajesh
Batchjob to load payslips for every month into DB | Payslips | Rajesh and Vinay
downloading the payslip from backend from employee dash board | Payslips | Umesh
REST service to process payslip downloading request | Payslips | Vinay
End to end integration | Payslips | Entire Team
Deployment of paylips feature in AWS | Payslips | Tirumala and Rajesh
Creation of DB schema for audit trail | Audit trail | Rajesh
Creation of UI to show audit history in app | Audit trail | Umesh
updating the create, update actions into audit trail table | Audit trail | Vinay
Fetching audit history from backend to diaply in audit trail UI | Audit trail | Umesh
REST service to process audit history request and send response in json format | Audit trail | Vinay
End to end integration | Audit trail | Tirumala and Rajesh
Deployment of audit trail in AWS | Audit trail | Entire Team
popup to show employee personal details in employee dashboard for view and update | EmployeeMaster | Umesh
Capturing any updated details in personal information by employee in employee dash board and sending the updated information to backend in json format | EmployeeMaster | Umesh
REST service to update the changes into DB | EmployeeMaster | Vinay
Popup to show HR touch points in employee dashboard | EmployeeMaster | Umesh
Cloud deployment | common | Tirumala
SMS gateway integration | common | Tirumala
Firewall issues | common | Tirumala

## Total estimate
RTS timesheet
start date | 2018-07-09
end date | 2018-07-20
Manual timesheet
start date | 2018-07-23
end date | 2018-08-03
Leaves
start date | 2018-08-06
end date | 2018-08-14
Useraccess management |  | Common
start date | 2018-07-16 | start date | 2018-07-09
end date | 2018-07-28 | end date | 2018-07-31
Employee Requests
start date | 2018-08-16
end date | 2018-08-24
Claims
start date | 2018-08-27
end date | 2018-08-31
Employee master
start date | 2018-09-03
end date | 2018-09-14
Client master
start date | 2018-09-17
end date | 2018-09-28
Payslips
start date | 2018-10-01
end date | 2018-10-05
Audit trail
start date | 2018-10-08
end date | 2018-10-15

## timesheets
Time sheet tasks
Task | Category | Assigned To | Estimate (in days)
HR timesheet dashboard UI (static) | HR timesheet dash board | Umesh | 2
Employee dash board UI (static) | Employee dash board | Umesh | 1
capturing RTS timehseet submitted by HR and sending to backend in json format | RTS timesheet | Umesh | 1
Finalizing manual timesheet template | ` | Entire Team | 2
capturing manual timehseet submitted by employee and sending to backend in json format | Manual timesheets | Umesh | 1
Popup to show the details of RTS report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh | 3
Pop to show the details of manual timesheet report results for errors, HR verified, pending etc.. | HR timesheet dash board | Umesh | 2
REST service to process json request for RTS timesheet | RTS timesheet | Vinay | 2
Validations of RTS timessheet for correct and wrong clockers and sending back result to front end | RTS timesheet | Vinay | 2
sending SMS regarding the timesheet status to employees | RTS timesheet | Vinay | 2
Saving the RTS timesheet details into DB | RTS timesheet | Vinay | 2
Saving the manual timesheet details into DB | Manual timesheets | Vinay | 2
Creation of timesheet DB schema | Manual timesheets | Rajesh | 1
Batch job to change the manual timesheet status from received to unprocessed every day night at 12:00 pm | Manual timesheets | Rajesh | 1
End to end integration | RTS timesheet | Entire Team | 2
Employee timesheet status query dashboard UI and displaying search results | Manual timesheets | Umesh | 2
REST service to service the search query for employee timesheet status query | Manual timesheets | Vinay | 2
Deployment of RTS timesheets feature in AWS | RTS timesheet | Tirumala and Rajesh | 1
End to end integration | Manual timesheets | Entire Team | 2
Deployment of manual timesheets feature in AWS | Manual timesheets | Tirumala and Rajesh | 1
SMS gateway integration | SMS gateway | Tirumala | 2
RTS timesheet
Start date = 09-07-2018
End date = 20-07-2018
Manual timesheet
Start date = 23-07-2018
End date = 03-08-2018

## Leaves
LEAVES
Task | Category | Assigned To | Estimate (in days)
Creation of employee leaves DB schema | Leaves | Rajesh | 1
Gathering leave records data for the current year from HR in the predetermined format | Leaves | Rajesh | 5
Batch job to load the leave history to DB | Leaves | Rajesh | 2
Getting employee leave details from back end and displaying in employee dashboard | Leaves | Umesh | 2
REST service to process employee leave details from RTS timesheet and updating DB | Leaves | Vinay | 2
UI to submit employee leave record in HR timesheet dashboard for manual timesheet employees | Leaves | Umesh | 1
Capturing employee leave record updated by HR from HR timesheet dashboard for manual timesheet employees and sending in JSON format to backend | Leaves | Umesh | 1
REST service to fecth the employee leave records from DB and sendig to front end in json format | Leaves | Vinay | 2
Fetching leave history from backend and displaying in employee dashboard | Leaves | Umesh | 2
End to end integration | Leaves | Entire Team | 2
Deployment of leaves feature in AWS | Leaves | Tirumala and Rajesh | 1
LEAVES
Start date = 06-08-2018
End date = 14-08-2018

## Useraccess management
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema | User access management | Rajesh | 2
Creation of new user UI | User access management | Umesh | 1
Capturing new user details and sending to back end in JSON fromat | User access management | Tirumala | 1
REST service to process new user request from front end and save in DB | User access management | Tirumala | 1
UI to add new roles to a user | User access management | Umesh | 1
Capturing new role details for a user and sending to backend in JSOn format | User access management | Tirumala | 1
REST service to process roles addition/updation request from front end and save in DB | User access management | Tirumala | 1
Setting permissions to each role (no UI required as of now) | User access management | Tirumala | 2
End to end integration | User access management | Entire team | 2
start date: 16-07-2018
end date : 28-07-2018

## Employee Requests
Employee Requests
Task | Category | Assigned To | Estimate (in days)
Creation of employee requests DB schema | Employee requests | Rajesh | 1
New employee request UI | Employee requests | Umesh | 1
Capturing the new employee request details and submitting to backend in JSON format | Employee requests | Umesh | 1
REST service to process the new employee request and updating the DB | Employee requests | Vinay | 1
Fetching the employee request processing activity from backend and displayed weekly activity dashboard | Employee requests | Umesh | 1
REST service to process the request for weekly activity dash board | Employee requests | Vinay | 2
Fetching the data for internal HR actions dashboard from back end and displaying dashboard | Employee requests | Umesh | 1
REST service to process the request for internal HR actions dashboard | Employee requests | Vinay | 1
Capturing the request status change in dashboard by HR and sending to backend in JSON format | Employee requests | Umesh | 1
REST service to process the request status and save in DB | Employee requests | Vinay | 2
End to end integration | Employee requests | Entire Team | 2
Deployment of requests feature in AWS | Employee requests | Tirumala and Rajesh | 1
Start date = 16-08-2018
end date = 24-08-2018

## Claims
Task | Category | Assigned To | Estimate (in days)
Creation of claims DB schema | Claims | Rajesh | 1
popup to show UI to upload new claim from employee dashboard | Claims | Umesh | 1
Capture the new claim details from claim UI and send to backend for saving into DB | Claims | Umesh | 1
REST service to process the new claim request from employee dashboard | Claims | Vinay | 2
Fetching the claim history data from back end and displaying cliams section of employee dashboard | Claims | Umesh | 2
Sending SMS to employee regarding their claim status | Claims | Vinay | 1
End to end integration | Claims | Entire team | 2
Deployment of claims feature in AWS | Claims | Tirumala and Rajesh | 1
Start date = 27-08-2018
End date = 31-08-02018

## Employeemaster
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Changing the employee creation UI with new changes(professional details and other changes in other sections) | EmployeeMaster | Umesh | 1
Capturing the employee details and sending to backend in JSON format | EmployeeMaster | Umesh | 2
Updating REST service to process the new employee details from employee master create section and save in DB | EmployeeMaster | Vinay | 2
Updating the existing employee DB schema as per the new changes in employee creation | EmployeeMaster | Rajesh | 1
updating the existing exmployee records in DB as per the new schema | EmployeeMaster | Rajesh | 7
end to end integration | EmployeeMaster | Entire team | 2
popup to show employee personal details in employee dashboard for view and update | EmployeeMaster | Umesh | 2
Capturing any updated details in personal information by employee in employee dash board and sending the updated information to backend in json format | EmployeeMaster | Umesh | 1
REST service to update the changes into DB | EmployeeMaster | Vinay | 1
Popup to show HR touch points in employee dashboard | EmployeeMaster | Umesh | 1
start date = 03-09-2018
end date = 14-09-2018
* Rajesh will start collecting the data from much earlier.

## Client Master
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Client master DB schema | Client Master | Rajesh | 2
Client master UI for creating clients | Client Master | Umesh | 3
Capturing client master details from create UI and sending to backend in JSON format | Client Master | Umesh | 2
REST service to process and save the new client details in client DB | Client Master | Vinay | 2
client search UI for viewing and updating exiting client in client master | Client Master | Umesh | 2
REST service to process client search query and send response in JSON format | Client Master | Vinay | 2
End to end integration | Client Master | Entire team | 2
Deployment of client master feature in AWS | Client Master | Tirumala and Rajesh | 1
start date = 17-09-2018
end date = 28-09-2018

## Payslips
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema for payslips | Payslips | Rajesh | 1
Loading three months payslips for preceding months | Payslips | Rajesh | 2
Batchjob to load payslips for every month into DB | Payslips | Rajesh and Vinay | 1
downloading the payslip from backend from employee dash board | Payslips | Umesh | 2
REST service to process payslip downloading request | Payslips | Vinay | 2
End to end integration | Payslips | Entire Team | 1
Deployment of paylips feature in AWS | Payslips | Tirumala and Rajesh | 1
start date = 1-10-2018
end date = 05-10-2018

## Audittrail
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Creation of DB schema for audit trail | Audit trail | Rajesh | 1
Creation of UI to show audit history in app | Audit trail | Umesh | 1
Updating the create, update actions into audit trail table | Audit trail | Vinay | 2
Fetching audit history from backend to display in audit trail UI | Audit trail | Umesh | 2
REST service to process audit history request and send response in json format | Audit trail | Vinay | 2
End to end integration | Audit trail | Tirumala and Rajesh | 1
Deployment of audit trail in AWS | Audit trail | Entire Team | 1
start date =08-10-2018
end date = 15-10-2018

## common
TOTAL TASKS
Task | Category | Assigned To | Estimate (in days)
Cloud deployment | common | Tirumala | 7
SMS gateway integration | common | Tirumala | 7
Firewall issues | common | Tirumala | 7
start date | 2018-07-09
end date | 2018-07-31